## Sheet1
Story ID | Story Name | As a/an | I want… | so that… | Priority | Iteration number | Acceptance Criteria | Date started | Date finished
1 | User function | user | Has a range of user functions | I can easily and easily operate the system. | 1 | 1
1.1 | Register system user | user | You can register an account when you use the system for the first time. | I can have the ability to use the banking system. | 1 | 1 | User will have data record after registering account | 2019-03-05 | 2019-03-24
1.1.1 | Registration information input prompt | user | The system can have tips to guide me how to register | I can complete registration quickly and easily. | 1 | 1 | There will be a message when the user clicks the registration option. | 2019-03-05 | 2019-03-24
1.1.2 | Registration success prompt | user | When I register successfully, the system will prompt you. | I can know if I successfully registered. | 2 | 1 | After the user successfully registers, the system interface will prompt | 2019-03-05 | 2019-03-24
1.2 | Log in to the system user | user | I can log in to the system after successful registration. | I can always operate the system | 1 | 1 |  | 2019-03-05 | 2019-03-24
1.2.1 | Login information input prompt | user | When logging in, the system has a prompt message prompting me how to log in. | I can complete the login quickly and easily. | 1 | 1 | When the user clicks Login, there will be a message input prompt. | 2019-03-05 | 2019-03-24
1.2.2 | Login success prompt | user | System login will be successful | I can know the status of my login success. | 2 | 1 | After the user logs in successfully, the system will prompt “Login Successful”. | 2019-03-05 | 2019-03-24
1.2.3 | Login failure prompt | user | Login failure will have a system prompt | I can know the status of my login failure. | 2 | 1 | After the user fails to log in, the message "Login failed, please re-enter" | 2019-03-05 | 2019-03-24
1.3 | New bank account | user | I can create multiple bank accounts to complete the transaction function. | I can execute the transaction | 1 | 2 |  | 2019-03-25 | 2019-04-07
1.3.1 | New bank account input information prompt | user | The system has a prompt message to remind me how to complete the account registration. | I can complete bank registration quickly and easily. | 1 | 2 | After registration, data will be stored in the user file. | 2019-03-25 | 2019-04-07
1.3.2 | Credit status inquiry | user | I can check my credit status at any time. | I can know if I can register a new bank account with the user. | 1 | 2 | Satisfied/unsatisfactory feedback after clicking on the credit status | 2019-03-25 | 2019-04-07
1.3.3 | Age judgment | user | Automatic judgment of age when creating a new bank account | I can know if I meet the age standard when I create a new junior account. | 2 | 2 | The age is automatically calculated based on the user input system | 2019-03-25 | 2019-04-07
1.3.4 | Account number and password prompt | user | I can know the account number and password after the new bank account. | I can use this information for the next login. | 1 | 2 | After creating a new account, the system will prompt the user to unique account number and password. | 2019-03-25 | 2019-04-07
1.4 | Log in to a bank account | user | I can log in to a bank account at any time to complete the relevant operations. | I can have a service about a bank account. | 1 | 2
1.4.1 | Login bank account information prompt | user | I can log in to my bank account quickly and easily. | I don't need to waste time logging into my account | 1 | 2 | When the user logs in to the account, the system will judge the correctness of the input information. | 2019-03-25 | 2019-04-07
1.4.2 | Bank account number matching prompt | user | The system will prompt if the account number exists. | I will not fill in the wrong account number | 2 | 2 | If the system does not find the account number match, it will report an error. | 2019-03-25 | 2019-04-07
1.4.3 | Login bank account success prompt | user | The system will prompt if the login is successful. | I can know my login status. | 2 | 2 | The system confirms that all the information matches and will print "Login Successful". | 2019-03-25 | 2019-04-07
1.5 | User detailed operation function | user | I have a range of useful functions | I can perform the function I want. | 1
1.5.1 | User deposit function | user | I can save money in my bank account. | I can increase my savings | 1 | 3 | After the user chooses to save the money, the balance value in the user's asking price will increase. | 2019-04-08 | 2019-04-28
1.5.1.3 | Deposit success balance prompt | user | There is a balance information prompt after the deposit is over. | I know how much money is left in my account. | 2 | 3 | The updated balance value in the user file is automatically read after the operation ends. | 2019-04-08 | 2019-04-28
1.5.1.4 | Uncleared funds prompt | user | The system has a check deposit function | Un-cleared amount information prompt after check deposit | 2 | 3 | The system will have cash / check option prompt information | 2019-04-08 | 2019-04-28
1.5.2 | User withdrawal function | user | I can withdraw money from my bank account. | I can use the money I took out | 1 | 3 | After withdrawing money, the balance value will decrease by the specified value. | 2019-04-08 | 2019-04-28
1.5.2.2 | Withdrawal guide step prompt | user | The system prompts how to withdraw funds | I can easily complete the withdrawal operation. | 1 | 3 | The system will have information to prompt the user what information to enter. | 2019-04-08 | 2019-04-28
1.5.2.4 | Successful withdrawal reminder | user | After the withdrawal is successful, there is a message prompt | I can know if I have successfully withdrawn | 2 | 3 | The system has information indicating the balance of the balance after withdrawal. | 2019-04-08 | 2019-04-28
1.5.3 | Suspend bank account function | user | I can suspend an account at any time. | I can lock this account and it's safer. | 1 | 3 | The account isSuspended value will change | 2019-04-08 | 2019-04-28
1.5.3.1 | Pause confirmation prompt | user | I will be prompted if I need to confirm the suspension of the account. | I can suspend my account in the middle of the reversal | 2 | 3 | There are options to prompt the user for input | 2019-04-08 | 2019-04-28
1.5.4 | Close bank account function | user | I can close an account at any time. | I can make this account never work. | 1 | 3 | Account isActive value will change | 2019-04-08 | 2019-04-28
1.5.4.1 | Balance information prompt before closing account | user | The system will prompt my account balance information before closing. | I can close my account after I withdraw my balance. | 3 | 3 | Clear the balance after confirmation | 2019-04-08 | 2019-04-28
1.5.4.2 | Close account confirmation | user | I will be prompted to confirm the closing of the account. | I can close the account in the middle of the operation. | 2 | 3 | There are options to prompt the user for input | 2019-04-08 | 2019-04-28
1.5.4.3 | Cannot be reused after closing account | employee | No further actions can be taken after closing the account | The account is completely invalid | 1 | 3 | The user will be prompted with an error message when selecting a service. | 2019-04-08 | 2019-04-28
1.5.5 | Exit system function | user | I can exit the system without selecting any service. | I can return to the previous service menu. | 3 | 3 | The system automatically jumps to the previous level | 2019-04-08 | 2019-04-28
2 | System administrator function | employee | I have some special features designed for administrators. | I can better manipulate user information | 1 | 4 |  | 2019-04-29 | 2019-05-12
2.1 | Check/update user credit status function | employee | I can check/update user credit status at any time. | I can know if I should create a new bank account for the user. | 1 | 4 | Satisfied/unsatisfactory feedback after clicking on the credit status | 2019-04-29 | 2019-05-12
2.1.2 | Credit status update boot step | employee | The system will prompt me how to update the user credit status. | I can update user credit status information quickly and easily. | 1 | 4 | There are options to prompt the user for input | 2019-04-29 | 2019-05-12
2.1.1 | Credit status check result feedback | employee | The system will tell the specific feedback after checking the user's credit status. | I can quickly and easily know the user's latest credit status information. | 2 | 4 | The system reads the credit status value in the user file and prints | 2019-04-29 | 2019-05-12
2.2 | Reinstate user account function | employee | After the user suspends a bank account, I can reinstate the account. | User can re-use the bank account | 1 | 4 | The account isSuspended value will change | 2019-04-29 | 2019-05-12
2.2.1 | Reinstate user bank account success prompt | employee | After reinstating user bank account, the system will prompt you | I can know if I successfully reinstate this account | 2 | 4 | System print read results | 2019-04-29 | 2019-05-12
[8 empty] | 2019-04-29 | 2019-05-12
2.3 | Clear funds function | employee | I can periodically clears un-cleared funds | Un-cleared funds are immediately credited to the account. | 1 | 4 | The un-clearedfunds variable in the user file will be 0, and the balance will be increased by the specified value. | 2019-04-29 | 2019-05-12
2.3.1 | Balance information after clear funds | employee | After clearing funds, the system can prompt the bank account for the latest balance information prompts. | I know if I have successfully cleared funds | 2 | 4 | The system has feedback information printed out | 2019-04-29 | 2019-05-12
2.4 | Have the same functionality as the user | employee | I can have the basic functions of a normal user. | I can help users quickly perform related operations. | 1 | 4 | The system enters the same user interface as the user | 2019-04-29 | 2019-05-12
2.5 | Exit system function | employee | I can quit the system halfway | I can return to the previous service menu. | 3 | 4 | The system automatically jumps to the previous level | 2019-04-29 | 2019-05-12